## Sheet1
Planned Timeline of Project
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Break 1 | Break 2 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
ConOps | bar: Week 1 to Week 3
Bill Of Materials | bar: Week 3 to Week 4
Systems Engineering Baseline
Functional Individual Components | bar: Week 2 to Week 6
Initial Prototype and Imaging Results | bar: Break 1 to Week 7
Final Prototype and Imaging Results | bar: Week 8 to Week 10
Showcase Poster | bar: Week 11 to Week 12
Technical Report | bar: Week 11 to Week 13
Handover with Client | bar: Week 13
Closing of Project | bar: Week 14
Actual Timeline of Project
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Break 1 | Break 2 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
ConOps | bar: Week 1 to Week 3
Bill Of Materials | bar: Week 3 to Week 6
Systems Engineering Baseline
Functional Individual Components | bar: Week 2 to Week 9
Initial Prototype and Imaging Results | bar: Week 10 to Week 11
Final Prototype and Imaging Results | bar: Week 10 to Week 11
Showcase Poster | bar: Week 10 to Week 11
Technical Report | bar: Week 12 to Week 13
Handover with Client | bar: Week 11 to Week 13
Closing of Project | bar: Week 14