## Task List
| Project Name | Portable EL device for PV testing
Project Manager
Date
Version
WORK BREAKDOWN STRUCTURE TEMPLATE - TASKS
Task No. | Task Description | Task Owner | Task Status | Due date | Notes
1 | Initiation and planning Phase
1.1 | Concept of Operations | Andrew, Balaji, Bhargav | Complete | 2023-03-10
1.2 | Bill of Materials | Andrew, Balaji, Bhargav | Complete | 2023-03-17
1.3 | System engineering baseline | Andrew, Balaji, Bhargav | In Progress | 2023-03-31
1.4 | Functional individual componenets | Whole team | In Progress | 2023-03-31
1.5 | early stage software process | Yixin, Levi, Zhengdao | In Progress | 2023-03-31
2 | Execution Phase
2.1 | initial software implementation | Yixin, Levi, Zhengdao, Andrew | In Progress | 2023-04-21
2.2 | Initial build of physical componenets | Bhargav, Balaji | In Progress | 2023-04-21
3 | Testing Phase
3.1 | Initial Prototyping | Whole team | In Progress | 2023-04-21
3.2 | Final prototyping and imaging test | Whole team | In Progress | 2023-05-12
3.3 | Compiling and analysing final results | Whole team | In Progress | 2023-05-12
4 | Close Phase
4.1 | Showcase poster | Whole team | In Progress | 2023-05-26
4.2 | Technical report | Whole team | In Progress | 2023-06-02
4.3 | Client handover | Whole team | In Progress | 2023-06-02

## WBS Tree
WBS TREE Diagram
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## How to Use WBS Template
How to Use Our WBS Template
The following is a breakdown of the terms and sections in the task list and WBS template.
Task No.: This is a numerical listing of the deliverable, which is further distinguished as you drill down deeper from task to subtask by decimal points to make sure you know exactly where in the process you are.
Task Description: This section details what the deliverable is and also goes into the task and the subtasks necessary to complete it.
Task Owner: Every deliverable, task and subtask needs an owner to make sure the work is getting done, and that person is noted in this column.
Dependency: Some tasks cannot be started until the task before them has been completed, which means it’s dependent on that task and they should be linked. This is the space where you can note task dependencies.
Resources Needed: Whatever the task needs in terms of people, equipment, materials, etc., is listed here.
Task Status: This is where you can track the status of a specific task or subtask. The dropdown menu gives you the option of marking the task as unassigned, assigned, in progress, late or complete.
Cost: Note the financial commitment needed to get the deliverable done.
Start Date: When did work on the deliverable begin? Mark it here.
Estimated Completion: The estimated amount of time allotted for the completion of the deliverable should be noted here.
Finish Date: When the deliverable is done, note the end date here.
Using the Tree Diagram
On the second sheet there is a tree chart to visualize the work breakdown structure, from the highest level at the top to the lowest level at the bottom, where the bottom is more specific and the top more general. You don’t have to add all the extra data you filled into the previous sheet, just the deliverable, task and how every many subtasks are needed to get the work done.